## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/maxExtentDate | assetLifetime/durationInDays | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_112 | Construction of 2 Evacuation Centres in Likangala and Chambo Wards | Multipurpose Evacuation Centers | Accommodate displaced flood victims usually occur along Likangala River | construction | completion | 2022-08-26T13:02:47Z | 2021-10-25T00:00:00Z | 2022-04-27T00:00:00Z | 2022-03-12T00:00:00Z | 138 | 2022-04-27T00:00:00Z | 2030-04-26T00:00:00Z | 2035-04-27T00:00:00Z | 4748 | 2021-03-10T00:00:00Z | 2022-10-24T00:00:00Z | 139440574.2 | MWK | 2022-04-27T00:00:00Z | Completed | Value excluding 5% Retention fee | Snagging | 50% of Retention released to cater for snag list within 12 months Defects Liability Period | 132468545.79 | MWK

## bud_bud_budgetBreakdown
id | budget/budgetBreakdowns/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/description | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/amount | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/currency | budget/budgetBreakdowns/0/budgetBreakdown/0/period/startDate | budget/budgetBreakdowns/0/budgetBreakdown/0/period/endDate | budget/budgetBreakdowns/0/budgetBreakdown/0/period/maxExtentDate | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/id | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/name
oc4ids-iuq5r5_112 | 1 | 98 | Construction of 2 Multipurpose Evacuation Centres | 139440574.2 | MWK | 2021-10-25T00:00:00Z | 2022-03-27T00:00:00Z | 2022-05-12T00:00:00Z | 96 | Fidelis Building Contractors

## bud_budgetBreakdowns
id | budget/budgetBreakdowns/0/id
oc4ids-iuq5r5_112 | 1

## con_sum_suppliers
id | contractingProcesses/0/id | contractingProcesses/0/summary/suppliers/0/id | contractingProcesses/0/summary/suppliers/0/name
oc4ids-iuq5r5_112 | 56 | 96 | Fidelis Building Contractors

## con_sum_ten_tenderers
id | contractingProcesses/0/id | contractingProcesses/0/summary/tender/tenderers/0/id | contractingProcesses/0/summary/tender/tenderers/0/name
oc4ids-iuq5r5_112 | 56 | 126 | ZOMBA CITY COUNCIL

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/procurementMethod | contractingProcesses/0/summary/tender/procurementMethodDetails | contractingProcesses/0/summary/tender/numberOfTenderers | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/maxExtentDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_112 | 56 | TD-OX/ZCC/21/172/LLW-MW/005 | Construction of 2 Evacuation Centres in Likangala and Chambo Wards | Retention Period | active | construction | open | bestProposal | 1 | 139440574 | MWK | 126 | ZOMBA CITY COUNCIL | 126 | ZOMBA CITY COUNCIL | 139440574 | MWK | 2021-10-25T00:00:00Z | 2022-03-27T00:00:00Z | 2022-05-12T00:00:00Z | 199

## locations
id | locations/0/id | locations/0/description | locations/0/geometry/type | locations/0/geometry/coordinates | locations/0/address/streetAddress | locations/0/address/locality | locations/0/address/region | locations/0/address/postalCode | locations/0/address/countryName
oc4ids-iuq5r5_112 | 147 | Construction of 2 Multipurpose Evacuation Centres | Point | 35.322332;-15.403515 | Chambo Ward | ZO | Southern | 0000 | Malawi
oc4ids-iuq5r5_112 | 148 | Construction of 2 Multipurpose Evacuation Centres | Point | 35.332117;-15.399171 | Likangala ward | ZO | Southern | 0000 | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/contactPoint/url | parties/0/roles | parties/0/contactPoint/faxNumber
oc4ids-iuq5r5_112 | 96 | Fidelis Building Contractors | P.O. Box 330, Zomba | Zomba | Southern Region | 0000 | Malawi | Fidelis Building Contractors | 0000 | 0000 | https://0000 | supplier
oc4ids-iuq5r5_112 | 126 | ZOMBA CITY COUNCIL | Off Nkulichi Road Opposite State House | Zomba City | Southern Region | 0000 | Malawi | ZOMBA CITY COUNCIL | fnankuyu@gmail.com | 0993383671 | https://0000 | tenderer;procuringEntity;administrativeEntity | 01525367