## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/durationInDays | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/endDateDetails | completion/finalScope | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_131 | Katsonga Girls Hostel fence | A fence for Katsonga girls hostel | for security | construction | completion | 2022-08-19T10:41:31Z | 2022-01-01T00:00:00Z | 2022-05-30T00:00:00Z | 2022-08-30T00:00:00Z | 241 | education | 2022-08-31T00:00:00Z | 2042-08-31T00:00:00Z | 7305 | 2021-09-08T00:00:00Z | 2021-09-08T00:00:00Z | 40612245.1 | MWK | 2022-08-30T00:00:00Z | fully constructed hostel fence | brick fence | 40612245.1 | MWK

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/datePublished | documents/0/dateModified | documents/0/format | documents/0/author
oc4ids-iuq5r5_131 | 37 | contractSigned | the contract for construction of Kasonga girls hostel fence at Malosa constituency- Kasonga ward | signed contract betweent Zomba District Council and Prichala Civil Engineering | https:// | 2021-12-01T00:00:00Z | 2021-12-01T00:00:00Z | application/pdf | zomba district council
oc4ids-iuq5r5_131 | 38 | negotiationParameters | contract negotiations on construction of Katsonga girls hostel fence | contract negotiations on construction of Katsonga girls hostel fence in Malosa constituency | https:// | 2021-12-24T00:00:00Z | 2021-12-24T00:00:00Z | application/pdf | zomba district council
oc4ids-iuq5r5_131 | 39 | awardNotice | Award of offer for construction of Katsonga girls hostel fence | award of offer for contsruction of Katsonga girls hostel fence in Malosa constituency | https:// | 2021-11-29T00:00:00Z | 2021-11-29T00:00:00Z | application/pdf | zomba district council

## locations
id | locations/0/id | locations/0/description | locations/0/address/locality | locations/0/address/region | locations/0/address/countryName
oc4ids-iuq5r5_131 | 119 | katsonga girls secondary school | ZO | Southern | Malawi