## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/durationInDays | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/endDateDetails | completion/finalScope | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_198 | Construction of Ndanga maternity Wing | Construction of Ndanga Maternity Wing | to improve maternal health | construction | completion | 2022-09-07T12:53:03Z | 2021-12-21T00:00:00Z | 2022-04-26T00:00:00Z | 126 | health | 2022-05-26T00:00:00Z | 2042-05-26T00:00:00Z | 7305 | 2021-09-28T00:00:00Z | 2021-12-06T00:00:00Z | 80000000 | MWK | 2022-05-11T00:00:00Z | a newly completed maternity wing | a new maternity wing | 72984781.01 | MWK

## bud_bud_budgetBreakdown
id | budget/budgetBreakdowns/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/description | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/amount | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/currency | budget/budgetBreakdowns/0/budgetBreakdown/0/period/startDate | budget/budgetBreakdowns/0/budgetBreakdown/0/period/endDate | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/id | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/name
oc4ids-iuq5r5_198 | 1 | 350 | The Project is located in T/A. Ndanga, Group Village Headman Ndanga along Phalombe-Chiradzulu road, in Mulanje North Constituencyloza Road in Mulanje District | 72984781.01 | MWK | 2021-12-21T00:00:00Z | 2022-02-22T00:00:00Z | 68 | Mulanje District Council

## bud_budgetBreakdowns
id | budget/budgetBreakdowns/0/id
oc4ids-iuq5r5_198 | 1

## con_sum_ten_tenderers
id | contractingProcesses/0/id | contractingProcesses/0/summary/tender/tenderers/0/id | contractingProcesses/0/summary/tender/tenderers/0/name
oc4ids-iuq5r5_198 | 485 | 162 | PCM Services

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/procurementMethod | contractingProcesses/0/summary/tender/procurementMethodDetails | contractingProcesses/0/summary/tender/numberOfTenderers | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_198 | 485 | MJDC2021-2022-Mw | Construction of Ndanga Maternity Wing | The project involved construction of a maternity wing at T/A. Ndanga in GVH Ndanga in Mulanje North Constituency | closed | construction | open | bestValueToGovernment | 1 | 72984781.01 | MWK | 68 | Mulanje District Council | 162 | PCM Services | 72984781.01 | MWK | 2021-12-21T00:00:00Z | 2022-02-22T00:00:00Z | 63

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_198 | 385 | contractSigned | Contract Agreement Form | The agreement was made on the 21st of December, 2021 between Mulanje District Council and PCM Services. | https:// | image/jpeg

## locations
id | locations/0/id | locations/0/description | locations/0/address/streetAddress | locations/0/address/locality | locations/0/address/region | locations/0/address/postalCode | locations/0/address/countryName
oc4ids-iuq5r5_198 | 561 | The Project is located in T/A. Ndanga, Group Village Headman Ndanga along Phalombe-Chiradzulu road, in Mulanje North Constituencyloza Road in Mulanje District | Along Phalombe-Chiradzulu road in T/A. Ndanga | MU | Southern | Private Bag 9, Mulanje | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles | parties/0/contactPoint/url
oc4ids-iuq5r5_198 | 68 | Mulanje District Council | along Kara O Mulla road | Mulanje | Southern | Private Bag 9 | Malawi | Mulanje District Council | mulanjecouncil@gov.mw | 09000000000 | procuringEntity
oc4ids-iuq5r5_198 | 162 | PCM Services | 0000 | Zomba | Southern Region | 0000 | Malawi | PCM Services | 0000 | 0000 | contractor;tenderer;administrativeEntity | https://0000