## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/maxExtentDate | assetLifetime/durationInDays | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/endDateDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_286 | Construction of Nalunga Police Senior Staff House | Construction of Staff House at Nalunga Police Unit | Construction of a House | construction | completion | 2025-05-22T15:33:44Z | 2023-02-21T00:00:00Z | 2023-05-20T00:00:00Z | 2023-05-30T00:00:00Z | 98 | socialHousing | 2023-02-21T00:00:00Z | 2073-05-30T00:00:00Z | 2073-05-30T00:00:00Z | 18361 | 2023-02-10T00:00:00Z | 2023-02-15T00:00:00Z | 71585854.44 | MWK | 2023-05-31T00:00:00Z | the project has been completed | 118175328.3 | MWK

## bud_bud_budgetBreakdown
id | budget/budgetBreakdowns/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/description | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/amount | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/currency | budget/budgetBreakdowns/0/budgetBreakdown/0/period/startDate | budget/budgetBreakdowns/0/budgetBreakdown/0/period/endDate | budget/budgetBreakdowns/0/budgetBreakdown/0/period/maxExtentDate | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/id | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/name
oc4ids-iuq5r5_286 | 1 | 180 | Contract Amount | 70585854.44 | MWK | 2023-02-06T00:00:00Z | 2023-05-17T00:00:00Z | 2023-06-30T00:00:00Z | 41 | Dowa District Council

## bud_budgetBreakdowns
id | budget/budgetBreakdowns/0/id
oc4ids-iuq5r5_286 | 1

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_286 | 150 | contractSigned | Contract Agreement | Contract Agreement | https:// | application/pdf

## locations
id | locations/0/id | locations/0/description | locations/0/address/streetAddress | locations/0/address/locality | locations/0/address/region | locations/0/address/postalCode | locations/0/address/countryName
oc4ids-iuq5r5_286 | 279 | Dowa East Constituency | Nalunga Trading Center, TA Chiwere | DO | Central | 0000 | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles | parties/0/contactPoint/url
oc4ids-iuq5r5_286 | 41 | Dowa District Council | Private Bag 2 | Dowa | Central | Dowa | Malawi | Dowa District Council | bandanoelsk@live.com | 0999632510 | procuringEntity
oc4ids-iuq5r5_286 | 45 | World Bank | 1818 H Street, NW Washington, DC 20433 USA | Washington, DC | District of Columbia | 20433 | United States of America (the) | World Bank | info@worldbank.org | +1 (202) 473-1000 | funder | https://www.worldbank.org
oc4ids-iuq5r5_286 | 258 | Eunick | Dowa | Dowa |  |  | Malawi | Eunick | bandanoelsk@live.com | 000000 | contractor