## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | assetLifetime/endDate | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_308 | Makumbo U5 Clinic Staff House | Construction of Makumbo U5 Clinic Staff House in TA Zilakoma, Tukombo Ward, South Constituency | To provide accommodation for health workers | construction | completion | 2023-04-11T07:13:34Z | 2021-07-01T00:00:00Z | 2022-06-30T00:00:00Z | 2022-07-31T00:00:00Z | 395 | health | 2073-07-30T00:00:00Z | 2020-05-26T00:00:00Z | 2020-06-10T00:00:00Z | 27699975 | MWK | 2022-06-30T00:00:00Z | The project was completed on 30th June 2022 | the project was completed within the specified contract amount | 27699975.81 | MWK

## con_sum_ten_tenderers
id | contractingProcesses/0/id | contractingProcesses/0/summary/tender/tenderers/0/id | contractingProcesses/0/summary/tender/tenderers/0/name
oc4ids-iuq5r5_308 | 404 | 263 | Nkhotakota District Council

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/externalReference | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/procurementMethod | contractingProcesses/0/summary/tender/procurementMethodDetails | contractingProcesses/0/summary/tender/numberOfTenderers | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/maxExtentDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_308 | 404 | 308 | NB/DC/GESD/2021/22/10/23 | construction of nkhwali clinic | construction of nkhwali clinic | active | construction | open | lowestCost | 1 | 64000000 | MWK | 263 | Nkhotakota District Council | 263 | Nkhotakota District Council | 64000000 | MWK | 2022-01-14T00:00:00Z | 2022-05-14T00:00:00Z | 2022-05-14T00:00:00Z | 120

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles
oc4ids-iuq5r5_308 | 263 | Nkhotakota District Council | Nkhotakota | Nkhotakota | Central | Malawi | Nkhotakota District Council | johnmanda92@gmail.com | 0999091707/0882376941 | tenderer;procuringEntity;administrativeEntity