## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/maxExtentDate | assetLifetime/durationInDays | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/endDateDetails
oc4ids-iuq5r5_316 | Construction of Iponga CDA Staff House | Construction of Iponga CDA Staff house in Karonga District | Provision of Accommodation for the Community development Assistant | construction | completion | 2023-06-02T11:43:37Z | 2022-12-21T00:00:00Z | 2023-04-20T00:00:00Z | 2023-04-30T00:00:00Z | 130 | socialHousing | 2022-12-21T00:00:00Z | 2046-07-20T00:00:00Z | 2063-04-20T00:00:00Z | 14730 | 2022-11-10T00:00:00Z | 2022-11-30T00:00:00Z | 46032665 | MWK | 2023-05-05T00:00:00Z | Project completed successfully

## bud_bud_budgetBreakdown
id | budget/budgetBreakdowns/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/description | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/amount | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/currency | budget/budgetBreakdowns/0/budgetBreakdown/0/period/startDate | budget/budgetBreakdowns/0/budgetBreakdown/0/period/endDate | budget/budgetBreakdowns/0/budgetBreakdown/0/period/maxExtentDate | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/id | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/name
oc4ids-iuq5r5_316 | 1 | 275 | Construction of Community Development Assistant's House | 46032665.97 | MWK | 2022-12-21T00:00:00Z | 2023-04-10T00:00:00Z | 2023-05-30T00:00:00Z | 235 | Mujolume Building Contractor

## bud_budgetBreakdowns
id | budget/budgetBreakdowns/0/id
oc4ids-iuq5r5_316 | 1

## con_sum_suppliers
id | contractingProcesses/0/id | contractingProcesses/0/summary/suppliers/0/id | contractingProcesses/0/summary/suppliers/0/name
oc4ids-iuq5r5_316 | 355 | 234 | Selemunthu Building Contractors

## con_sum_ten_tenderers
id | contractingProcesses/0/id | contractingProcesses/0/summary/tender/tenderers/0/id | contractingProcesses/0/summary/tender/tenderers/0/name
oc4ids-iuq5r5_316 | 355 | 235 | Mujolume Building Contractor

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/externalReference | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/procurementMethod | contractingProcesses/0/summary/tender/procurementMethodDetails | contractingProcesses/0/summary/tender/numberOfTenderers | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/maxExtentDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_316 | 355 | KADC/GESD/IPONGA STAFF-H/2022-23/03 | KADC/GESD/IPONGA STAFF-H/2022-23/03 | Construction of Iponga CDA Staff | Construction of Community Development Assistant's house | active | construction | direct | lowestCost | 1 | 46032665.97 | MWK | 55 | Karonga District Council | 55 | Karonga District Council | 46032665.97 | MWK | 2022-12-22T00:00:00Z | 2023-04-10T00:00:00Z | 2023-05-30T00:00:00Z | 159

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/datePublished | documents/0/dateModified | documents/0/format
oc4ids-iuq5r5_316 | 210 | contractAnnexe | Construction of Iponga CDA Staff | Current status of Iponga CDA Staff House | https:// | 2023-06-02T00:00:00Z | 2023-06-02T00:00:00Z | image/jpeg
oc4ids-iuq5r5_316 | 211 | contractAnnexe | Construction of Iponga CDA Staff | current project status | https:// | 2023-06-02T00:00:00Z | 2023-06-02T00:00:00Z | image/jpeg
oc4ids-iuq5r5_316 | 212 | contractSigned | Construction of CDA Staff House | Signed contract Documentation for the construction of the CDA House | https:// | 2023-06-02T00:00:00Z | 2023-06-02T00:00:00Z | application/pdf

## locations
id | locations/0/id | locations/0/description | locations/0/address/locality | locations/0/address/region | locations/0/address/countryName
oc4ids-iuq5r5_316 | 388 | North of Karonga Boma, near the Songwe Boader | KR | Northern | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles
oc4ids-iuq5r5_316 | 55 | Karonga District Council | P.O. Box 35, Karonga | Karonga | Northern Region | 0000 | Malawi | Karonga District Council | Email@email.com | 00000000 | administrativeEntity;procuringEntity
oc4ids-iuq5r5_316 | 234 | Selemunthu Building Contractors | Karonga | Karonga | North |  | Malawi | Selemunthu Building Contractors | mail@mail.com | 0999623869 | supplier
oc4ids-iuq5r5_316 | 235 | Mujolume Building Contractor | Mzuzu | Mzuzu | North |  | Malawi | Mujolume Building Contractor | exprin | 0881246087 | contractor;tenderer