## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/maxExtentDate | assetLifetime/durationInDays | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/endDateDetails | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_324 | Construction of Chitipa Bus Depot (First Phase) | The project will include the construction of a fence, gate, and guard room and the renovation of the old market shed into a depot shed | The project will provide a conducive environment for people to board buses and provides security to passengers and their goods | construction | implementation | 2023-04-11T09:58:03Z | 2023-01-19T00:00:00Z | 2023-05-30T00:00:00Z | 2023-06-30T00:00:00Z | 162 | transport.road | 2023-04-15T00:00:00Z | 2050-05-30T00:00:00Z | 2055-05-30T00:00:00Z | 11733 | 2022-12-15T00:00:00Z | 2022-11-29T00:00:00Z | 40000000 | MWK | 2023-04-15T00:00:00Z | The project is currently ongoing and is at 50% | The construction of fence is at super structure level Construction of the guard room is at slab level Construction of market masters office and two shops at slab level | 40000000 | MWK

## bud_bud_budgetBreakdown
id | budget/budgetBreakdowns/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/description | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/amount | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/currency | budget/budgetBreakdowns/0/budgetBreakdown/0/period/startDate | budget/budgetBreakdowns/0/budgetBreakdown/0/period/endDate | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/id | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/name
oc4ids-iuq5r5_324 | 1 | 295 | The Funding is from DDF and it comprises of Preliminaries, fence and gate 50%, Guard room and bus shelter renovation 45%, and retention 5% | 40000000 | MWK | 2023-01-26T00:00:00Z | 2023-03-27T00:00:00Z | 62 | Chitipa District Council

## bud_budgetBreakdowns
id | budget/budgetBreakdowns/0/id
oc4ids-iuq5r5_324 | 1

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_324 | 385 | Contract/19/01/23 | Contract | Project contract details | active | construction | 40000000 | MWK | 62 | Chitipa District Council | 62 | Chitipa District Council | 40000000 | MWK | 2023-01-26T00:00:00Z | 2023-03-27T00:00:00Z | 60

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_324 | 277 | contractSigned | Contract | Project contract document | https:// | application/pdf
oc4ids-iuq5r5_324 | 278 | defaultEvents | Picture | Almost completed phase one of the bus depot | https:// | image/jpeg

## locations
id | locations/0/id | locations/0/description | locations/0/address/locality | locations/0/address/region | locations/0/address/countryName
oc4ids-iuq5r5_324 | 422 | Chitipa Boma, TA MWABULAMBIA | CT | Northern | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles | parties/0/contactPoint/faxNumber
oc4ids-iuq5r5_324 | 62 | Chitipa District Council | P.O. Box 1, Chitipa | Chitipa | Northern Region | 0000 | Malawi | Chitipa District Council | Email@email.com | 00000000 | procuringEntity;administrativeEntity
oc4ids-iuq5r5_324 | 232 | B&R Construction | area 3 | LILONGWE | Central | Box 30895 | Malawi | B&R Construction | brconstruction@gmail.com | 0884377135 | contractor | 0000