## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_379 | Rehabilitation of Chandawe Health Post- Maternity Wing | The project sought to rehabilitate the maternity wing at Chandawe Health Post | Reduce Mother and Infant mortality rate, through provision of conducive environment for child delivery. | rehabilitation | completion | 2023-05-17T16:16:19Z | 2021-12-29T00:00:00Z | 2022-03-31T00:00:00Z | 2022-03-31T00:00:00Z | 92 | health | 2021-04-01T00:00:00Z | 2021-12-01T00:00:00Z | 23000000 | MWK | 2022-03-31T00:00:00Z | Works 100 % done. Ceiling, Plumbing, Wards Demarcation, Rest and Bath Rooms Construction, Drainage Works, Sluice Room Furnishing and Finishing Works done | An addendum of MWK4,010,000 was made | Health | 25088462 | MWK

## bud_bud_budgetBreakdown
id | budget/budgetBreakdowns/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/description | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/amount | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/currency | budget/budgetBreakdowns/0/budgetBreakdown/0/period/startDate | budget/budgetBreakdowns/0/budgetBreakdown/0/period/endDate | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/id | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/name
oc4ids-iuq5r5_379 | 1 | 205 | Approved Budget | 23000000 | MWK | 2021-12-29T00:00:00Z | 2022-03-31T00:00:00Z | 20 | Ntchisi District Council
oc4ids-iuq5r5_379 | 1 | 206 | Total Project Cost | 25088462 | MWK | 2021-12-29T00:00:00Z | 2022-03-31T00:00:00Z | 20 | Ntchisi District Council
oc4ids-iuq5r5_379 | 1 | 214 | Expenditure | 24665495.09 | MWK | 2021-12-29T00:00:00Z | 2022-03-31T00:00:00Z | 20 | Ntchisi District Council

## bud_budgetBreakdowns
id | budget/budgetBreakdowns/0/id
oc4ids-iuq5r5_379 | 1

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_379 | 151 | NS/IPDAC/GESD/WKS/2021-22/01-LOT 7 | Contract Agreement Between Ntchisi District Council and Marcus Constructiom | The contract states that Marcus Construction is to Executive the rehabilitation of Chandawe Health Post | closed | construction | 23000000 | MWK | 20 | Ntchisi District Council | 20 | Ntchisi District Council | 21078462.5 | MWK | 2021-12-29T00:00:00Z | 2022-03-31T00:00:00Z | 92

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_379 | 163 | environmentalImpact | ESMP for the rehabilitation of Chandawe Health Post | The document describes in detail the potential environmental and social impacts associated with the proposed sub project under rehabilitation of Chandawe Health Post and outline mitigation measures required to address the identified impacts | https:// | application/vnd.openxmlformats-officedocument.wordprocessingml.document
oc4ids-iuq5r5_379 | 178 | contractSigned | Contract Agreement NS & Marcus Construction- Rehabilitation of Chandawe Health Post- Maternity Wing | This is the signed Contract Agreement between Ntchisi District Council and Marcus Construction- Rehabilitation of Chandawe Health Post- Maternity Wing | https:// | application/msword
oc4ids-iuq5r5_379 | 179 | contractSigned | Contract Agreement NS & Marcus Construction- Rehabilitation of Chandawe Health Post- Maternity Wing | This is the signed Contract Agreement between Ntchisi District Council and Marcus Construction- Rehabilitation of Chandawe Health Post- Maternity Wing | https:// | application/msword

## locations
id | locations/0/id | locations/0/description | locations/0/address/locality | locations/0/address/region | locations/0/address/countryName
oc4ids-iuq5r5_379 | 313 | T/A Chilooko | NI | Central | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles
oc4ids-iuq5r5_379 | 20 | Ntchisi District Council | Box 1 | Ntchisi | Central | Malawi | Ntchisi District Council | email@email.com | 000000000 | procuringEntity;administrativeEntity