## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/durationInDays | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/endDateDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_395 | Masangano Classroom block | Construction of a classroom block at Masangano to cater to 120 students | To increase the number of classrooms and reduction in Pupil congestion. | construction | completion | 2023-05-17T16:20:09Z | 2021-12-29T00:00:00Z | 2022-03-31T00:00:00Z | 92 | 2021-04-01T00:00:00Z | 2021-12-01T00:00:00Z | 32815617 | MWK | 2022-03-31T00:00:00Z | Substructure and Superstructure Works done. Roofing, Flooring and Finishing Works done | 32815617 | MWK

## bud_bud_budgetBreakdown
id | budget/budgetBreakdowns/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/description | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/amount | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/currency | budget/budgetBreakdowns/0/budgetBreakdown/0/period/startDate | budget/budgetBreakdowns/0/budgetBreakdown/0/period/endDate | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/id | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/name
oc4ids-iuq5r5_395 | 1 | 209 | Approved Budget | 17440000 | MWK | 2021-12-29T00:00:00Z | 2022-03-31T00:00:00Z | 20 | Ntchisi District Council
oc4ids-iuq5r5_395 | 1 | 210 | Total Project Cost | 32815617 | MWK | 2021-12-29T00:00:00Z | 2022-03-31T00:00:00Z | 20 | Ntchisi District Council
oc4ids-iuq5r5_395 | 1 | 211 | Expenditure | 26007060 | MWK | 2021-12-29T00:00:00Z | 2022-03-31T00:00:00Z | 20 | Ntchisi District Council

## bud_budgetBreakdowns
id | budget/budgetBreakdowns/0/id
oc4ids-iuq5r5_395 | 1

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_395 | 134 | NS/IPDAC/GESD/WKS/2021-22/01-LOT 3 | Contract Agreement between Hiltons Construction and Ntchisi District Council | The agreement stated thatHiltons Construction wll construct Classroom Blocks at Masangano School | closed | 32815717 | MWK | 20 | Ntchisi District Council | 20 | Ntchisi District Council | 32815617 | MWK | 2021-12-29T00:00:00Z | 2022-03-31T00:00:00Z | 92

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_395 | 148 | environmentalImpact | ESMP For Masangano Classroom block | The document describes in detail the potential environmental and social impacts associated with the proposed sub project under Masangano School block construction and outline mitigation measures required to address the identified impacts | https:// | application/vnd.openxmlformats-officedocument.wordprocessingml.document
oc4ids-iuq5r5_395 | 176 | contractSigned | Contract Agreement- NS & Hiltons Construction-Masangano Classroom block | This is the signed Contract Agreement between Ntchisi District Council and Hiltons Construction for the construction of Masangano Classroom block | https:// | application/msword

## locations
id | locations/0/id | locations/0/description | locations/0/address/locality | locations/0/address/countryName
oc4ids-iuq5r5_395 | 291 | T/A Kalumo | NI | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles
oc4ids-iuq5r5_395 | 20 | Ntchisi District Council | Box 1 | Ntchisi | Central | Malawi | Ntchisi District Council | email@email.com | 000000000 | procuringEntity;administrativeEntity