## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/maxExtentDate | assetLifetime/durationInDays | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency
oc4ids-iuq5r5_450 | Construction of Laboratory / Library blocks in 29 Selected Community Day Secondary Schools. | Construction of Laboratory and Library blocks | To increase access and equity to secondary education for all eligible students, with particular focus on girls, vulnerable groups and other categories of students that find access difficult, including those travelling longer distances in rural areas. | construction | implementation | 2023-05-17T20:16:21Z | 2017-04-01T00:00:00Z | 2017-10-01T00:00:00Z | 2024-03-31T00:00:00Z | 2556 | education | 2024-03-31T00:00:00Z | 2074-03-31T00:00:00Z | 2074-03-31T00:00:00Z | 18262 | 2017-03-01T00:00:00Z | 2017-07-01T00:00:00Z | 5000000000 | MWK

## con_sum_suppliers
id | contractingProcesses/0/id | contractingProcesses/0/summary/suppliers/0/id | contractingProcesses/0/summary/suppliers/0/name
oc4ids-iuq5r5_450 | 181 | 350 | FUKUMELE BUILDING CONTRACTORS
oc4ids-iuq5r5_450 | 182 | 349 | ANDREW AND ANDREW BUILDING CONTRACTORS
oc4ids-iuq5r5_450 | 183 | 313 | CK Construction
oc4ids-iuq5r5_450 | 184 | 313 | CK Construction
oc4ids-iuq5r5_450 | 185 | 313 | CK Construction
oc4ids-iuq5r5_450 | 186 | 310 | Chipesi Building Contractors
oc4ids-iuq5r5_450 | 187 | 97 | PBM Construction
oc4ids-iuq5r5_450 | 188 | 300 | Kokoliko Construction
oc4ids-iuq5r5_450 | 189 | 314 | Building Masters and Catoi Joint Venture
oc4ids-iuq5r5_450 | 192 | 116 | Opco Limited
oc4ids-iuq5r5_450 | 193 | 116 | Opco Limited
oc4ids-iuq5r5_450 | 194 | 294 | OPCO Limited
oc4ids-iuq5r5_450 | 195 | 310 | Chipesi Building Contractors
oc4ids-iuq5r5_450 | 196 | 310 | Chipesi Building Contractors
oc4ids-iuq5r5_450 | 197 | 297 | Rays Construction
oc4ids-iuq5r5_450 | 198 | 348 | PROJECTS BUILDING CONTRACTORS
oc4ids-iuq5r5_450 | 199 | 98 | ACH Limited
oc4ids-iuq5r5_450 | 200 | 302 | Mpumila Building Contractors
oc4ids-iuq5r5_450 | 201 | 305 | Cooperative and Elyon Joint Venture
oc4ids-iuq5r5_450 | 202 | 305 | Cooperative and Elyon Joint Venture
oc4ids-iuq5r5_450 | 203 | 305 | Cooperative and Elyon Joint Venture
oc4ids-iuq5r5_450 | 204 | 164 | Shireco Construction
oc4ids-iuq5r5_450 | 205 | 164 | Shireco Construction
oc4ids-iuq5r5_450 | 206 | 164 | Shireco Construction
oc4ids-iuq5r5_450 | 207 | 295 | Tapita/Donekis Construction
oc4ids-iuq5r5_450 | 208 | 295 | Tapita/Donekis Construction
oc4ids-iuq5r5_450 | 209 | 295 | Tapita/Donekis Construction

## con_sum_ten_tenderers
id | contractingProcesses/0/id | contractingProcesses/0/summary/tender/tenderers/0/id | contractingProcesses/0/summary/tender/tenderers/0/name
oc4ids-iuq5r5_450 | 185 | 267 | Ministry of Education

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/maxExtentDate | contractingProcesses/0/summary/contractPeriod/durationInDays | contractingProcesses/0/summary/tender/procurementMethod | contractingProcesses/0/summary/tender/procurementMethodDetails | contractingProcesses/0/summary/tender/numberOfTenderers
oc4ids-iuq5r5_450 | 181 | 025/IPC/MOEST/EIMU/CW/2015-16 | Construction of Laboratory Library block at Namatubi Community Day Secondary School in Chitipa | Construction of Laboratory and Library block | active | construction | 267 | Ministry of Education | 267 | Ministry of Education | 86827690.95 | MWK | 2017-04-01T00:00:00Z | 2017-10-01T00:00:00Z | 2024-03-31T00:00:00Z | 2556
oc4ids-iuq5r5_450 | 182 | 025/IPC/MOEST/EIMU/CW/2015-16 | Construction of Laboratory Library block at Iponga Community Day Secondary School in Karonga | Construction of Laboratory / Library block | active | construction | 267 | Ministry of Education | 267 | Ministry of Education | 81782954.38 | MWK | 2017-04-01T00:00:00Z | 2017-10-01T00:00:00Z | 2024-03-31T00:00:00Z | 2556
oc4ids-iuq5r5_450 | 183 | 025/IPC/MOEST/EIMU/CW/2015-16 | Construction of Laboratory Library block at Mlowe Community Day Secondary School in Rumphi | Construction of Laboratory / Library block | active | construction | 267 | Ministry of Education | 267 | Ministry of Education | 69810955.55 | MWK | 2017-04-01T00:00:00Z | 2017-10-01T00:00:00Z | 2024-03-31T00:00:00Z | 2556
oc4ids-iuq5r5_450 | 184 | 025/IPC/MOEST/EIMU/CW/2015-16 | Construction of Laboratory Library block at Luzi Community Day Secondary School in Mzimba | Construction of Laboratory / Library block | active | construction | 267 | Ministry of Education | 267 | Ministry of Education | 74577121.27 | MWK | 2017-04-01T00:00:00Z | 2017-10-01T00:00:00Z | 2024-03-31T00:00:00Z | 2556
oc4ids-iuq5r5_450 | 185 | 025/IPC/MOEST/EIMU/CW/2015-16 | Construction of Laboratory Library block at Chitheka Community Day Secondary School in Nkhatabay | Construction of Laboratory / Library block | active | construction | 267 | Ministry of Education | 267 | Ministry of Education | 79791646.28 | MWK | 2017-04-01T00:00:00Z | 2017-10-01T00:00:00Z | 2024-03-31T00:00:00Z | 2556 | open | bestValueToGovernment | 1
oc4ids-iuq5r5_450 | 186 | 025/IPC/MOEST/EIMU/CW/2015-16 | Construction of Laboratory Library block at Chamakala Community Day Secondary School in Kasungu | Construction of Laboratory / Library block | active | construction | 267 | Ministry of Education | 267 | Ministry of Education | 83570705.8 | MWK | 2017-04-01T00:00:00Z | 2017-10-01T00:00:00Z |  | 183
oc4ids-iuq5r5_450 | 187 | 025/IPC/MOEST/EIMU/CW/2015-16 | Construction of Laboratory Library block at Natola Community Day Secondary School in Dowa | Construction of Laboratory / Library block | active | construction | 267 | Ministry of Education | 267 | Ministry of Education | 86594678.47 | MWK | 2017-04-01T00:00:00Z | 2017-10-01T00:00:00Z | 2024-03-31T00:00:00Z | 2556
oc4ids-iuq5r5_450 | 188 | 025/IPC/MOEST/EIMU/CW/2015-16 | Construction of Laboratory Library block at Mpherere Community Day Secondary School in Ntchisi | Construction of Laboratory / Library block | active | construction | 267 | Ministry of Education | 267 | Ministry of Education | 76840833.8 | MWK | 2017-04-01T00:00:00Z | 2017-10-01T00:00:00Z | 2024-03-31T00:00:00Z | 2556
oc4ids-iuq5r5_450 | 189 | 025/IPC/MOEST/EIMU/CW/2015-16 | Construction of Laboratory Library block at Sopa Community Day Secondary School in Mchinji | Construction of Laboratory / Library block | active | construction | 267 | Ministry of Education | 267 | Ministry of Education | 83560642 | MWK | 2017-04-01T00:00:00Z | 2017-10-01T00:00:00Z | 2024-03-31T00:00:00Z | 2556
oc4ids-iuq5r5_450 | 190 | 025/IPC/MOEST/EIMU/CW/2015-16 | Construction of Laboratory Library block at Chimwa Community Day Secondary School in Lilongwe | Construction of Laboratory / Library block | active | construction | 267 | Ministry of Education | 267 | Ministry of Education | 114784124.54 | MWK | 2017-04-01T00:00:00Z | 2017-10-01T00:00:00Z | 2024-03-31T00:00:00Z | 2556
oc4ids-iuq5r5_450 | 191 | 025/IPC/MOEST/EIMU/CW/2015-16 | Construction of Laboratory Library block at MAFCO Community Day Secondary School in Salima | Construction of Laboratory / Library block | active | construction | 267 | Ministry of Education | 267 | Ministry of Education | 75350669.95 | MWK | 2017-04-01T00:00:00Z | 2017-10-01T00:00:00Z | 2024-03-31T00:00:00Z | 2556
oc4ids-iuq5r5_450 | 192 | 12 | Construction of Laboratory Library block at Mtakataka Community Day Secondary School in Dedza | Construction of Laboratory / Library block | active | construction |  |  | 267 | Ministry of Education | 94506679.52 | MWK | 2017-04-01T00:00:00Z | 2017-10-01T00:00:00Z | 2024-03-31T00:00:00Z | 2556
oc4ids-iuq5r5_450 | 193 | 025/IPC/MOEST/EIMU/CW/2015-16 | Construction of Laboratory Library block at Linga Community Day Secondary School in Nkhotakota | Construction of Laboratory / Library block | active | construction | 267 | Ministry of Education | 267 | Ministry of Education | 90619316.45 | MWK | 2017-04-01T00:00:00Z | 2017-10-01T00:00:00Z | 2024-03-31T00:00:00Z | 2556
oc4ids-iuq5r5_450 | 194 | 025/IPC/MOEST/EIMU/CW/2015-16 | Construction of Laboratory Library block at Kapudzama Community Day Secondary School in Lilongwe | Construction of Laboratory / Library block | active | construction | 267 | Ministry of Education | 267 | Ministry of Education | 91396200.29 | MWK | 2017-04-01T00:00:00Z | 2017-10-01T00:00:00Z | 2024-03-31T00:00:00Z | 2556
oc4ids-iuq5r5_450 | 195 | 025/IPC/MOEST/EIMU/CW/2015-16 | Construction of Laboratory Library block at Kalaka Community Day Secondary School in Ntcheu | Construction of Laboratory / Library block | active | construction | 267 | Ministry of Education | 267 | Ministry of Education | 84774829.43 | MWK | 2017-04-01T00:00:00Z | 2017-10-01T00:00:00Z | 2024-03-31T00:00:00Z | 2556
oc4ids-iuq5r5_450 | 196 | 025/IPC/MOEST/EIMU/CW/2015-16 | Construction of Laboratory Library block at Ngombechinda Community Day Secondary School in Mzimba | Construction of Laboratory / Library block | active | construction | 267 | Ministry of Education | 267 | Ministry of Education | 84645579.43 | MWK | 2017-04-01T00:00:00Z | 2017-10-01T00:00:00Z | 2024-03-31T00:00:00Z | 2556
oc4ids-iuq5r5_450 | 197 | 025/IPC/MOEST/EIMU/CW/2015-16 | Construction of Laboratory Library block at Kapire Community Day Secondary School in Mangochi | Construction of Laboratory / Library block | active | construction | 267 | Ministry of Education | 267 | Ministry of Education | 86681054.96 | MWK | 2017-04-01T00:00:00Z | 2017-10-01T00:00:00Z | 2024-03-31T00:00:00Z | 2556
oc4ids-iuq5r5_450 | 198 | 025/IPC/MOEST/EIMU/CW/2015-16 | Construction of Laboratory Library block at Ulumba Community Day Secondary School in Zomba | Construction of Laboratory / Library block | active | construction | 267 | Ministry of Education | 267 | Ministry of Education | 83109571.11 | MWK | 2017-04-01T00:00:00Z | 2017-10-01T00:00:00Z | 2024-03-31T00:00:00Z | 2556
oc4ids-iuq5r5_450 | 199 | 025/IPC/MOEST/EIMU/CW/2015-16 | Construction of Laboratory Library block at Misanjo Community Day Secondary School in Mulanje | Construction of Laboratory / Library block | active | construction | 267 | Ministry of Education | 267 | Ministry of Education | 80887747.18 | MWK | 2017-04-01T00:00:00Z | 2017-10-01T00:00:00Z | 2024-03-31T00:00:00Z | 2556
oc4ids-iuq5r5_450 | 200 | 025/IPC/MOEST/EIMU/CW/2015-16 | Construction of Laboratory Library block at Livunzu Community Day Secondary School in Chikwawa | Construction of Laboratory / Library block | active | construction | 267 | Ministry of Education | 267 | Ministry of Education | 77270807.08 | MWK | 2017-04-01T00:00:00Z | 2017-10-01T00:00:00Z | 2024-03-31T00:00:00Z | 2556
oc4ids-iuq5r5_450 | 201 | 025/IPC/MOEST/EIMU/CW/2015-16 | Construction of Laboratory Library block at Chinolampeni Community Day Secondary School in Phalombe | Construction of Laboratory / Library block | active | construction | 267 | Ministry of Education | 267 | Ministry of Education | 80337885.02 | MWK | 2017-04-01T00:00:00Z | 2017-10-01T00:00:00Z | 2024-03-31T00:00:00Z | 2556
oc4ids-iuq5r5_450 | 202 | 025/IPC/MOEST/EIMU/CW/2015-16 | Construction of Laboratory Library block at Ntambanyama Community Day Secondary School in Thyolo | Construction of Laboratory / Library block | active | construction | 267 | Ministry of Education | 267 | Ministry of Education | 85110919.49 | MWK | 2017-04-01T00:00:00Z | 2017-10-01T00:00:00Z | 2024-03-31T00:00:00Z | 2556
oc4ids-iuq5r5_450 | 203 | 025/IPC/MOEST/EIMU/CW/2015-16 | Construction of Laboratory Library block at Ntenjera Community Day Secondary School in Blantyre | Construction of Laboratory / Library block | active | construction | 267 | Ministry of Education | 267 | Ministry of Education | 76676258.37 | MWK | 2017-04-01T00:00:00Z | 2017-10-01T00:00:00Z | 2024-03-31T00:00:00Z | 2556
oc4ids-iuq5r5_450 | 204 | 025/IPC/MOEST/EIMU/CW/2015-16 | Construction of Laboratory Library block at Lisungwi Community Day Secondary School in Neno | Construction of Laboratory / Library block | active | construction | 267 | Ministry of Education | 267 | Ministry of Education | 70844922.84 | MWK | 2017-04-01T00:00:00Z | 2017-10-01T00:00:00Z | 2024-03-31T00:00:00Z | 2556
oc4ids-iuq5r5_450 | 205 | 025/IPC/MOEST/EIMU/CW/2015-16 | Construction of Laboratory Library block at Mphande Community Day Secondary School in Mwanza | Construction of Laboratory / Library block | active | construction | 267 | Ministry of Education | 267 | Ministry of Education | 70370179.87 | MWK | 2017-04-01T00:00:00Z | 2017-10-01T00:00:00Z | 2024-03-31T00:00:00Z | 2556
oc4ids-iuq5r5_450 | 206 | 025/IPC/MOEST/EIMU/CW/2015-16 | Construction of Laboratory Library block at Mapesi Community Day Secondary School in Kasungu | Construction of Laboratory / Library block | active | construction | 267 | Ministry of Education | 267 | Ministry of Education | 77710456.65 | MWK | 2018-07-01T00:00:00Z | 2017-10-01T00:00:00Z | 2024-03-31T00:00:00Z | 2100
oc4ids-iuq5r5_450 | 207 | 025/IPC/MOEST/EIMU/CW/2015-16 | Construction of Laboratory Library block at Rivirivi Community Day Secondary School in Balaka | Construction of Laboratory / Library block | active | construction | 267 | Ministry of Education | 267 | Ministry of Education | 74480291.54 | MWK | 2017-04-01T00:00:00Z | 2017-10-01T00:00:00Z | 2024-03-31T00:00:00Z | 2556
oc4ids-iuq5r5_450 | 208 | 025/IPC/MOEST/EIMU/CW/2015-16 | Construction of Laboratory Library block at Mpiranjala Community Day Secondary School in Machinga | Construction of Laboratory / Library block | active | construction | 267 | Ministry of Education | 267 | Ministry of Education | 74480291.54 | MWK | 2017-04-01T00:00:00Z | 2017-10-01T00:00:00Z | 2024-03-31T00:00:00Z | 2556
oc4ids-iuq5r5_450 | 209 | 025/IPC/MOEST/EIMU/CW/2015-16 | Construction of Laboratory Library block at Kalambo Community Day Secondary School in Nsanje | Construction of Laboratory / Library block | active | construction | 267 | Ministry of Education | 267 | Ministry of Education | 84048108.96 | MWK | 2017-04-01T00:00:00Z | 2017-10-01T00:00:00Z | 2024-03-31T00:00:00Z | 2556

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/contactPoint/url | parties/0/roles
oc4ids-iuq5r5_450 | 97 | PBM Construction | P.O. 31495 | Lilongwe | Central Region | 0000 | Malawi | PBM Construction | 0000 | 0000 | https://0000 | supplier
oc4ids-iuq5r5_450 | 98 | ACH Limited | P.O. Box 3005 | Blantyre | Southern Region |  | Malawi | ACH Limited | 0000 | 0000 | https://0000 | supplier
oc4ids-iuq5r5_450 | 116 | Opco Limited | P.O. Box 5132, Limbe, Blantyre | Blantyre | Southern Region | 0000 | Malawi | Opco Limited | 0000 | 0000 | https://0000 | supplier
oc4ids-iuq5r5_450 | 164 | Shireco Construction | P.O.Box 1369, Blantyre | Blantyre | Southern Region | 0000 | Malawi | Shireco Construction | 0000 | +265 999 931 829 | https://0000 | supplier
oc4ids-iuq5r5_450 | 267 | Ministry of Education | Lilongwe | Lilongwe |  |  | Malawi | Ministry of Education | dgshh@gmai.mw | 000 |  | tenderer;procuringEntity;administrativeEntity
oc4ids-iuq5r5_450 | 294 | OPCO Limited | Lilongwe | Lilongwe |  |  | Malawi | OPCO Limited | @gmail.com | 0000 |  | supplier
oc4ids-iuq5r5_450 | 295 | Tapita/Donekis Construction | Lilongwe | Lilongwe |  |  | Malawi | Tapita/Donekis Construction | @gmail.com | 0000 |  | supplier
oc4ids-iuq5r5_450 | 297 | Rays Construction | Lilongwe | Lilongwe |  |  | Malawi | Rays Construction | @gmail.com | 0000 |  | supplier
oc4ids-iuq5r5_450 | 300 | Kokoliko Construction | Lilongwe | Lilongwe |  |  | Malawi | Kokoliko Construction | @gmail.com | 0000 |  | supplier
oc4ids-iuq5r5_450 | 302 | Mpumila Building Contractors | Lilongwe | Lilongwe |  |  | Malawi | Mpumila Building Contractors | @gmail.com | 0000 |  | supplier
oc4ids-iuq5r5_450 | 305 | Cooperative and Elyon Joint Venture | Lilongwe | Lilongwe |  |  | Malawi | Cooperative and Elyon Joint Venture | @gmail.com | 0000 |  | supplier
oc4ids-iuq5r5_450 | 310 | Chipesi Building Contractors | Lilongwe | Lilongwe |  |  | Malawi | Chipesi Building Contractors | @gmail.com | 0000 |  | supplier
oc4ids-iuq5r5_450 | 313 | CK Construction | Lilongwe | Lilongwe |  |  | Malawi | CK Construction | @gmail.com | 0000 |  | supplier
oc4ids-iuq5r5_450 | 314 | Building Masters and Catoi Joint Venture | Lilongwe | Lilongwe |  |  | Malawi | Building Masters and Catoi Joint Venture | @gmail.com | 0000 |  | supplier
oc4ids-iuq5r5_450 | 348 | PROJECTS BUILDING CONTRACTORS | Lilongwe | Lilongwe |  |  | Malawi | PROJECTS BUILDING CONTRACTORS | @gmail.com | 0000 |  | supplier
oc4ids-iuq5r5_450 | 349 | ANDREW AND ANDREW BUILDING CONTRACTORS | Lilongwe | Lilongwe |  |  | Malawi | ANDREW AND ANDREW BUILDING CONTRACTORS | @gmail.com | 0000 |  | supplier
oc4ids-iuq5r5_450 | 350 | FUKUMELE BUILDING CONTRACTORS | Lilongwe | Lilongwe |  |  | Malawi | FUKUMELE BUILDING CONTRACTORS | @gmail.com | 0000 |  | supplier