## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/durationInDays | sector | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_515 | Construction of Mbalachanda Police Unit Block | Construction of police unit and double hole pit latrine using cement blocks. | Improving security levels in the surrounding area. | construction | completion | 2023-06-03T07:20:22Z | 2021-12-19T00:00:00Z | 2022-02-27T00:00:00Z | 70 | governance | 2021-09-09T00:00:00Z | 2021-11-11T00:00:00Z | 23203057.56 | MWK | 2022-02-28T00:00:00Z | The project is still under completion stage as the building developed some defects of which the contractor is yet to fix. | None. | The contractor is yet to fix the defects. | The contractor is yet to fix the defects. | 23203057.56 | MWK

## con_sum_suppliers
id | contractingProcesses/0/id | contractingProcesses/0/summary/suppliers/0/id | contractingProcesses/0/summary/suppliers/0/name
oc4ids-iuq5r5_515 | 366 | 248 | Pyramid Building and Civil Engineering

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_515 | 366 | MDC/NCB/GESD/2021/22/08 | contract details | contract details | closed | construction | 23203057.56 | MWK | 54 | M'mbelwa District Council | 54 | M'mbelwa District Council | 23203057.56 | MWK | 2021-12-19T00:00:00Z | 2022-02-27T00:00:00Z | 70

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_515 | 238 | contractSigned | Contract agreement | Contract agreement. | https:// | application/pdf
oc4ids-iuq5r5_515 | 239 | minutes | Site meeting minutes | Site meeting minutes. | https:// | application/vnd.openxmlformats-officedocument.wordprocessingml.document

## locations
id | locations/0/id | locations/0/description | locations/0/address/locality | locations/0/address/region | locations/0/address/countryName
oc4ids-iuq5r5_515 | 412 | Mbalachanda Ward, T/A Chindi, Mbalachanda trading centre | MZ | Northern | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/contactPoint/url | parties/0/roles | parties/0/contactPoint/faxNumber
oc4ids-iuq5r5_515 | 45 | World Bank | 1818 H Street, NW Washington, DC 20433 USA | Washington, DC | District of Columbia | 20433 | United States of America (the) | World Bank | info@worldbank.org | +1 (202) 473-1000 | https://www.worldbank.org | funder
oc4ids-iuq5r5_515 | 54 | M'mbelwa District Council | P.O. Box 132, Mzimba | Mzimba | Northern Region | 0000 | Malawi | M'mbelwa District Council | Email@email.com | 00000000 |  | administrativeEntity;procuringEntity;tenderer
oc4ids-iuq5r5_515 | 248 | Pyramid Building and Civil Engineering | Lilongwe street | LILONGWE | central | P.O. Box 31137, Lilongwe | Malawi | Pyramid Building and Civil Engineering | pyramidbuilding@gmail.com | 0888909960 |  | contractor;supplier | 0000
oc4ids-iuq5r5_515 | 265 | National Local Goverment | Lilongwe | Lilongwe |  |  | Malawi | National Local Goverment | gsgsf@mnd.com | 000 |  | reviewBody