## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/durationInDays | sector | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_519 | Renovation of clinic and staff house completion at Wateleka Health Post | Rehabilitation of an existing health post building and completion of a staff house. | Improve health outcomes of people in the area by reducing the distance Mzimba district hospital. | rehabilitation | completion | 2023-06-02T11:08:32Z | 2021-12-20T00:00:00Z | 2022-02-18T00:00:00Z | 60 | health | 2021-09-09T00:00:00Z | 2021-11-11T00:00:00Z | 15478603 | MWK | 2022-03-18T00:00:00Z | All construction works were completed. | None | All works were satisfactorily done. | The project is functional. | 15478603 | MWK

## bud_bud_budgetBreakdown
id | budget/budgetBreakdowns/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/description | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/amount | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/currency | budget/budgetBreakdowns/0/budgetBreakdown/0/period/startDate | budget/budgetBreakdowns/0/budgetBreakdown/0/period/endDate | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/id | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/name
oc4ids-iuq5r5_519 | 1 | 281 | Budget breakdown of the project | 15478603 | MWK | 2021-12-12T00:00:00Z | 2022-02-18T00:00:00Z | 54 | M'mbelwa District Council

## bud_budgetBreakdowns
id | budget/budgetBreakdowns/0/id
oc4ids-iuq5r5_519 | 1

## con_sum_suppliers
id | contractingProcesses/0/id | contractingProcesses/0/summary/suppliers/0/id | contractingProcesses/0/summary/suppliers/0/name
oc4ids-iuq5r5_519 | 365 | 356 | Kanthukako

## con_sum_ten_tenderers
id | contractingProcesses/0/id | contractingProcesses/0/summary/tender/tenderers/0/id | contractingProcesses/0/summary/tender/tenderers/0/name
oc4ids-iuq5r5_519 | 365 | 54 | M'mbelwa District Council

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/procurementMethod | contractingProcesses/0/summary/tender/procurementMethodDetails | contractingProcesses/0/summary/tender/numberOfTenderers | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_519 | 365 | MDC/NCB/GESD/2021/22/09 | Contract details | Contract details. | closed | construction | open | ratedCriteria | 1 | 15478603 | MWK | 54 | M'mbelwa District Council | 54 | M'mbelwa District Council | 15478603 | MWK | 2021-12-12T00:00:00Z | 2022-02-18T00:00:00Z | 68

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_519 | 235 | contractSigned | Contract agreement | Contract agreement | https:// | application/pdf
oc4ids-iuq5r5_519 | 236 | completionCertificate | Completion certificate | Completion certificate. | https:// | application/pdf
oc4ids-iuq5r5_519 | 237 | minutes | Project minutes | Site meeting minutes. | https:// | application/vnd.openxmlformats-officedocument.wordprocessingml.document

## locations
id | locations/0/id | locations/0/description | locations/0/address/locality | locations/0/address/region | locations/0/address/countryName
oc4ids-iuq5r5_519 | 411 | Wateleka, TA Mzikubola | MZ | Northern | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/contactPoint/url | parties/0/roles
oc4ids-iuq5r5_519 | 45 | World Bank | 1818 H Street, NW Washington, DC 20433 USA | Washington, DC | District of Columbia | 20433 | United States of America (the) | World Bank | info@worldbank.org | +1 (202) 473-1000 | https://www.worldbank.org | funder
oc4ids-iuq5r5_519 | 54 | M'mbelwa District Council | P.O. Box 132, Mzimba | Mzimba | Northern Region | 0000 | Malawi | M'mbelwa District Council | Email@email.com | 00000000 |  | administrativeEntity;procuringEntity;tenderer
oc4ids-iuq5r5_519 | 265 | National Local Goverment | Lilongwe | Lilongwe |  |  | Malawi | National Local Goverment | gsgsf@mnd.com | 000 |  | reviewBody
oc4ids-iuq5r5_519 | 356 | Kanthukako | mzimba | mzimba |  |  | Malawi | Kanthukako | @gmail.com | 00000 |  | contractor;supplier