## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/durationInDays | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/durationInDays | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_520 | Construction of girls Hostel at Misiku CDSS | The project will construct an eighty-bed hostel | To promote girl child education as they are provided with decent accommodation within the school premises hence averting other social and physical distractors on their education | construction | completion | 2023-06-02T11:09:33Z | 2022-01-01T00:00:00Z | 2022-04-01T00:00:00Z | 90 | 2022-04-01T00:00:00Z | 2123-04-01T00:00:00Z | 36889 | 2021-11-01T00:00:00Z | 2021-01-01T00:00:00Z | 51624823.65 | MWK | 2023-03-09T00:00:00Z | The girl's hostel is fully completed and within the defects liability timelines | 51,624,823.65 | The completion certificate not issued | The eighty-bed hostel constructed | 51624823.65 | MWK

## bud_bud_budgetBreakdown
id | budget/budgetBreakdowns/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/description | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/amount | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/currency | budget/budgetBreakdowns/0/budgetBreakdown/0/period/startDate | budget/budgetBreakdowns/0/budgetBreakdown/0/period/endDate | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/id | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/name
oc4ids-iuq5r5_520 | 1 | 288 | The Funding is from GESD and it comprises of Substructure 30%, Superstructure and roof 38%, finishing and retention 32% | 51624823.65 | MWK | 2022-01-01T00:00:00Z | 2022-04-01T00:00:00Z | 62 | Chitipa District Council

## bud_budgetBreakdowns
id | budget/budgetBreakdowns/0/id
oc4ids-iuq5r5_520 | 1

## con_sum_suppliers
id | contractingProcesses/0/id | contractingProcesses/0/summary/suppliers/0/id | contractingProcesses/0/summary/suppliers/0/name
oc4ids-iuq5r5_520 | 359 | 330 | KABROS BUILDING CONTRACTORS

## con_sum_ten_tenderers
id | contractingProcesses/0/id | contractingProcesses/0/summary/tender/tenderers/0/id | contractingProcesses/0/summary/tender/tenderers/0/name
oc4ids-iuq5r5_520 | 359 | 330 | KABROS BUILDING CONTRACTORS

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/procurementMethod | contractingProcesses/0/summary/tender/procurementMethodDetails | contractingProcesses/0/summary/tender/numberOfTenderers | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_520 | 359 | Contract Addendum No1 | Contract details for Construction of girls hostel at Misuku CDSS | The project is completed | closed | construction | open | lowestCost | 1 | 51624823.65 | MWK | 62 | Chitipa District Council | 62 | Chitipa District Council | 51624823.65 | MWK | 2022-01-01T00:00:00Z | 2022-04-01T00:00:00Z | 90

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_520 | 259 | contractSigned | Contract | The contract between Chitipa District Council and Kabros Building Contractors to construct Misuku Girls Hostel at Misuku CDSS | https:// | application/pdf
oc4ids-iuq5r5_520 | 260 | contractSigned | Contract addendum | This addendum was made due to the inadequacy of funds for the completion of the project due to the devaluation of the Kwacha. | https:// | application/pdf
oc4ids-iuq5r5_520 | 261 | defaultEvents | Project Pictures | The picture shows the completed structure of the girls' hostel at Misuku CDSS captured during a joint monitoring visit organised by the council | https:// | image/jpeg

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles
oc4ids-iuq5r5_520 | 62 | Chitipa District Council | P.O. Box 1, Chitipa | Chitipa | Northern Region | 0000 | Malawi | Chitipa District Council | Email@email.com | 00000000 | procuringEntity;administrativeEntity
oc4ids-iuq5r5_520 | 330 | KABROS BUILDING CONTRACTORS | Lilongwe | Lilongwe |  |  | Malawi | KABROS BUILDING CONTRACTORS | @gmail.com | 0000 | contractor;tenderer;supplier