## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/durationInDays | sector | assetLifetime/startDate | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency | social/landCompensationBudget/amount | social/landCompensationBudget/currency | social/inIndigenousLand
oc4ids-iuq5r5_631 | Construction of Boma Shops | Constructing 5 shops and completing toilet block that was at window level. | Revenue generation for the council | construction | completion | 2023-09-06T08:50:56Z | 2023-01-18T00:00:00Z | 2023-05-18T00:00:00Z | 120 | economy | 2023-06-30T00:00:00Z | 2023-03-30T00:00:00Z | 2023-05-09T00:00:00Z | 60699999.76 | MWK | 2023-06-30T00:00:00Z | Completed | Within contract amount | Completed | Completed. Awaiting handover | 60652069.18 | MWK | 60699999.76 | MWK | TRUE

## bud_bud_budgetBreakdown
id | budget/budgetBreakdowns/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/description | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/amount | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/currency | budget/budgetBreakdowns/0/budgetBreakdown/0/period/startDate | budget/budgetBreakdowns/0/budgetBreakdown/0/period/endDate | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/id | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/name
oc4ids-iuq5r5_631 | 1 | 331 | Contract Reference Number | 60699999.76 | MWK | 2023-01-18T00:00:00Z | 2023-05-18T00:00:00Z | 369 | Mwanza District Council

## bud_budgetBreakdowns
id | budget/budgetBreakdowns/0/id
oc4ids-iuq5r5_631 | 1

## con_sum_suppliers
id | contractingProcesses/0/id | contractingProcesses/0/summary/suppliers/0/id | contractingProcesses/0/summary/suppliers/0/name
oc4ids-iuq5r5_631 | 533 | 96 | Fidelis Building Contractors

## con_sum_ten_tenderers
id | contractingProcesses/0/id | contractingProcesses/0/summary/tender/tenderers/0/id | contractingProcesses/0/summary/tender/tenderers/0/name
oc4ids-iuq5r5_631 | 533 | 96 | Fidelis Building Contractors
oc4ids-iuq5r5_631 | 533 | 381 | LD Building and Civil Engineering
oc4ids-iuq5r5_631 | 533 | 382 | TIYESEMBO BUILDING CONTRACTOR

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/durationInDays | contractingProcesses/0/summary/tender/procurementMethod | contractingProcesses/0/summary/tender/procurementMethodDetails | contractingProcesses/0/summary/tender/numberOfTenderers
oc4ids-iuq5r5_631 | 462 | MW-MDC 318973-CW-RFQ | Construction of shops | Signed contract | active | construction | 60699999.76 | MWK | 369 | Mwanza District Council | 369 | Mwanza District Council | 60699999.76 | MWK | 2023-01-18T00:00:00Z | 2023-05-18T00:00:00Z | 120
oc4ids-iuq5r5_631 | 533 | MW-MDC318973-CW-RFQ | Construction of Mwanza Boma Shops | New construction of 5 shops block at Mwanza boma with associated toilet and external paving works | closed | construction | 65000000 | MWK | 369 | Mwanza District Council | 369 | Mwanza District Council | 60699999.76 | MWK | 2023-01-17T00:00:00Z | 2023-04-17T00:00:00Z | 90 | open | bestValueToGovernment | 3

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_631 | 377 | contractSigned | Contract Agreement for Boma shops | Signed contract for Construction of Boma shops | https:// | application/pdf
oc4ids-iuq5r5_631 | 513 | feasibilityStudy | BOMA SHOPS | CONSTRUCTION OF BOMA SHOPS | https:// | application/pdf
oc4ids-iuq5r5_631 | 515 | environmentalImpact | BOMA SHOPS | CONSTRUCTION OF BOMA SHOPS | https:// | application/pdf
oc4ids-iuq5r5_631 | 516 | socialImpact | BOMA SHOPS | CONSTRUCTION OF BOMA SHOPS | https:// | application/pdf

## locations
id | locations/0/id | locations/0/description | locations/0/address/locality | locations/0/address/region | locations/0/address/countryName
oc4ids-iuq5r5_631 | 534 | TA Kanduku, GVH Mchotseni | MW | Southern | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/contactPoint/url | parties/0/roles
oc4ids-iuq5r5_631 | 96 | Fidelis Building Contractors | P.O. Box 330, Zomba | Zomba | Southern Region | 0000 | Malawi | Fidelis Building Contractors | 0000 | 0000 | https://0000 | contractor;tenderer;supplier
oc4ids-iuq5r5_631 | 369 | Mwanza District Council | Mwanza | Mwanza |  |  | Malawi | Mwanza District Council | @gmail.com | 000 |  | procuringEntity;administrativeEntity
oc4ids-iuq5r5_631 | 381 | LD Building and Civil Engineering | Blantyre | Blantyre |  |  | Malawi | LD Building and Civil Engineering | @gmail.com | 0000 |  | tenderer
oc4ids-iuq5r5_631 | 382 | TIYESEMBO BUILDING CONTRACTOR | Nsanje | Nsanje |  |  | Malawi | TIYESEMBO BUILDING CONTRACTOR | @gmail.com | 0000 |  | tenderer

## soc_consultationMeetings
id | social/consultationMeetings/0/id | social/consultationMeetings/0/date | social/consultationMeetings/0/numberOfParticipants | social/consultationMeetings/0/address/streetAddress | social/consultationMeetings/0/address/locality | social/consultationMeetings/0/address/region | social/consultationMeetings/0/address/countryName
oc4ids-iuq5r5_631 | 21 | 2023-01-20T00:00:00Z | 21 | Boma shops | Mchosteni | Southern | Malawi
oc4ids-iuq5r5_631 | 22 | 2023-04-21T00:00:00Z | 10 | Shops site | Mchotseni | Southern | Malawi