## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/maxExtentDate | assetLifetime/durationInDays | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/endDateDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency | social/inIndigenousLand
oc4ids-iuq5r5_668 | Construction of Mgomwa Market Shed | Construction of the market Shed, and double hole VIP Toilet | Improve Market Infrastructure, sanitation and hygiene | construction | decommissioning | 2025-08-14T14:55:28Z | 2023-06-19T00:00:00Z | 2023-09-19T00:00:00Z | 2023-11-30T00:00:00Z | 164 | economy | 2023-09-19T00:00:00Z | 2038-09-30T00:00:00Z | 2040-09-30T00:00:00Z | 6221 | 2022-12-05T00:00:00Z | 2022-12-06T00:00:00Z | 25319254.5 | MWK | 2023-10-05T00:00:00Z | completed all works | Market Shed and 2-hole VIP Toilet | Market Shed and 2-hole VIP Toilet | 26383113.5 | MWK | TRUE

## ben_beneficiaries
id | benefits/0/beneficiaries/0/description | benefits/0/beneficiaries/0/numberOfPeople
oc4ids-iuq5r5_668 | Vendors for vegetables and assorted item | 144

## benefits
id | benefits/0/title | benefits/0/description
oc4ids-iuq5r5_668 | Mgomwa Market Beneficiaries | VMgomwa vendors

## con_sum_suppliers
id | contractingProcesses/0/id | contractingProcesses/0/summary/suppliers/0/id | contractingProcesses/0/summary/suppliers/0/name
oc4ids-iuq5r5_668 | 520 | 388 | TWENDE CONTRACTORS

## con_sum_ten_tenderers
id | contractingProcesses/0/id | contractingProcesses/0/summary/tender/tenderers/0/id | contractingProcesses/0/summary/tender/tenderers/0/name
oc4ids-iuq5r5_668 | 520 | 333 | LEONOR ENG LIMITED
oc4ids-iuq5r5_668 | 520 | 236 | Marogo Civil & Building Contractors
oc4ids-iuq5r5_668 | 520 | 385 | Marshall Construction
oc4ids-iuq5r5_668 | 520 | 162 | PCM Services
oc4ids-iuq5r5_668 | 520 | 388 | TWENDE CONTRACTORS

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/procurementMethod | contractingProcesses/0/summary/tender/procurementMethodDetails | contractingProcesses/0/summary/tender/numberOfTenderers | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/maxExtentDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_668 | 520 | BDC/DDF/W/2023 | Contract | Contract Details for Mgomwa | closed | construction | open | bestValueToGovernment | 5 | 30000000 | MWK | 69 | Balaka District Council | 69 | Balaka District Council | 26383113.5 | MWK | 2023-07-03T00:00:00Z | 2023-10-30T00:00:00Z | 2023-12-29T00:00:00Z | 179

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_668 | 457 | environmentalImpact | Mgomwa Environmental and Social Screening Form | Environmental and Social Screening | https:// | application/pdf
oc4ids-iuq5r5_668 | 458 | feasibilityStudy | Feasibility Study Report | Site technical Assessment report | https:// | application/pdf
oc4ids-iuq5r5_668 | 459 | completionCertificate | Mgomwa Completion Certificate | Completion Certificate | https:// | application/pdf
oc4ids-iuq5r5_668 | 460 | valueForMoneyAnalysis | Site Appraisal Form | Site Appraisal for cost-benefit analysis | https:// | application/pdf
oc4ids-iuq5r5_668 | 461 | socialImpact | Social Impact Assessment | Mgomwa Environmental and Social Impact Assessment | https:// | application/pdf
oc4ids-iuq5r5_668 | 462 | costBenefitAnalysis | Mgomwa Cost Benefit Analysis | Mgomwa Cost Benefit Analysis | https:// | application/pdf
oc4ids-iuq5r5_668 | 485 | maintenancePlan | Maintenance Plan | Building Maintenance plan | https:// | application/pdf

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/contactPoint/faxNumber | parties/0/contactPoint/url | parties/0/roles
oc4ids-iuq5r5_668 | 69 | Balaka District Council | off balaka main road next to Meru filling station | Balaka | South | P/Bag 1 | Malawi | Balaka District Council | gamafrancis6@gmail.com | 265 1 552 049 | 265 1 552 050/790 | http://balakadistrictcouncil.com | administrativeEntity;procuringEntity
oc4ids-iuq5r5_668 | 162 | PCM Services | 0000 | Zomba | Southern Region | 0000 | Malawi | PCM Services | 0000 | 0000 |  | https://0000 | tenderer
oc4ids-iuq5r5_668 | 236 | Marogo Civil & Building Contractors | Mchinji Boma | Mchinji | Central | Box 28 | Malawi | Marogo Civil & Building Contractors | marogo@gmail.com | 0880927578 | 0000 |  | tenderer
oc4ids-iuq5r5_668 | 333 | LEONOR ENG LIMITED | Lilongwe | Lilongwe |  |  | Malawi | LEONOR ENG LIMITED | @gmail.com | 0000 |  |  | tenderer
oc4ids-iuq5r5_668 | 385 | Marshall Construction | Zomba | Zomba |  |  | Malawi | Marshall Construction | @gmail.com | 0000 |  |  | tenderer
oc4ids-iuq5r5_668 | 388 | TWENDE CONTRACTORS | Mangochi | Mangochi |  |  | Malawi | TWENDE CONTRACTORS | @gmail.com | 0000 |  |  | contractor;tenderer;supplier

## soc_consultationMeetings
id | social/consultationMeetings/0/id | social/consultationMeetings/0/date | social/consultationMeetings/0/numberOfParticipants | social/consultationMeetings/0/address/streetAddress | social/consultationMeetings/0/address/locality | social/consultationMeetings/0/address/region | social/consultationMeetings/0/address/countryName
oc4ids-iuq5r5_668 | 1 | 2023-08-30T00:00:00Z | 7 | Mgowma Market Shed | Mgomwa | South | Malawi