## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_702 | Completion of Thambani Police staff house | This project invlves completion of police staff housing at Thambani police unit which failed to completed year ago | To reduce housing challenges among police officers | construction | completion | 2023-09-06T12:47:54Z | 2022-10-01T00:00:00Z | 2022-12-30T00:00:00Z | 2023-02-28T00:00:00Z | 150 | governance | 2023-09-06T00:00:00Z | 2023-09-06T00:00:00Z | 5500000 | MWK | 2023-02-28T00:00:00Z | Completed | It was not completed within the contract amount due to inflation but also transition from works contract to labour contract during the completion stage | Completed | Completed | 5500000 | MWK

## bud_bud_budgetBreakdown
id | budget/budgetBreakdowns/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/id | budget/budgetBreakdowns/0/budgetBreakdown/0/description | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/amount | budget/budgetBreakdowns/0/budgetBreakdown/0/amount/currency | budget/budgetBreakdowns/0/budgetBreakdown/0/period/startDate | budget/budgetBreakdowns/0/budgetBreakdown/0/period/endDate | budget/budgetBreakdowns/0/budgetBreakdown/0/period/maxExtentDate | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/id | budget/budgetBreakdowns/0/budgetBreakdown/0/sourceParty/name
oc4ids-iuq5r5_702 | 1 | 341 | Contract Reference Number | 5500000 | MWK | 2022-10-01T00:00:00Z | 2022-12-30T00:00:00Z | 2023-02-28T00:00:00Z | 369 | Mwanza District Council

## bud_budgetBreakdowns
id | budget/budgetBreakdowns/0/id
oc4ids-iuq5r5_702 | 1

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/maxExtentDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_702 | 477 | RFQ/MNDC/W/2021-22/28 | Contract Agreement for Thambani police staff house | Contract and implementation period | closed | construction | 1500000 | MWK | 383 | Solomoni Khutamowa | 369 | Mwanza District Council | 1500000 | MWK | 2022-10-01T00:00:00Z | 2022-12-30T00:00:00Z | 2023-02-28T00:00:00Z | 150

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_702 | 375 | contractSigned | Contract Agreement for Thambani police staff house | Signed contract | https:// | application/pdf

## locations
id | locations/0/id | locations/0/description | locations/0/address/locality | locations/0/address/region | locations/0/address/countryName
oc4ids-iuq5r5_702 | 552 | Govati/Thambani | MW | Southern | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles
oc4ids-iuq5r5_702 | 369 | Mwanza District Council | Mwanza | Mwanza | Malawi | Mwanza District Council | @gmail.com | 000 | administrativeEntity
oc4ids-iuq5r5_702 | 383 | Solomoni Khutamowa | Mwanza | Mwanza | Malawi | Solomoni Khutamowa | @gmail.com | 0000 | contractor;procuringEntity