## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/durationInDays | sector | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_729 | Construction of 600mm Culvert Line at Gululu Stream | The project will involve the installation of Culvert line at Gululu stream | To ease transportation and communication | construction | completion | 2023-09-07T08:31:33Z | 2023-06-08T00:00:00Z | 2023-07-07T00:00:00Z | 29 | transport.road | 2023-06-12T00:00:00Z | 2023-06-14T00:00:00Z | 2998050 | MWK | 2023-07-07T00:00:00Z | The project completed successfully | Two million nine hundred ninety eight thousand and fifty kwacha. | The project completed successfully | The project completed successfully | 2998050 | MWK