## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/durationInDays | sector | budget/requestDate | budget/approvalDate | budget/amount/amount | budget/amount/currency | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_748 | Construction of 88 No 2 bedroomed semi detached at Area 49/5 in Lilongwe | Construction of 88 No 2 bedroomed semi detached houses | Providing shelter and affordable houses for the nation | construction | completion | 2023-09-07T16:00:55Z | 2019-03-29T00:00:00Z | 2020-01-15T00:00:00Z | 292 | socialHousing | 2018-12-20T00:00:00Z | 2019-02-01T00:00:00Z | 2101693601.94 | MWK | 2021-09-09T00:00:00Z | Late installation of utilities (water and ESCOM) Change of construction site | Change of construction site contributed to variation in cost due to ground conditions | Completion of 88No semi detached 2 bedroomed houses | Construction of 88No semi detached houses | 2223374616.98 | MWK