## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/durationInDays | budget | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_179 | Construction of a Classroom block at Kakolo Primary school | Construction of a two roomed classroom block | to reduce the high pupil to classroom ratio | construction | completion | 2022-08-29T10:36:40Z | 2021-12-29T00:00:00Z | 2022-03-29T00:00:00Z | 90 | education | 2022-03-24T00:00:00Z | 2062-03-24T00:00:00Z | 14610 | 0.00 | 2022-03-24T00:00:00Z | the project was completed on schedule | the project was completed over budget because of the rise in cost of construction materials | Construction of a classroom block | the scope did not change | 28344478.19 | MWK

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_179 | 67 | LDC/DDF/2021-22/CB/01D/2 | Construction of a Classroom block at Kakolo Primary school | the contract is not closed so as to enable change of scope | active | construction | 25000000 | MWK | 22 | Lilongwe District Council | 22 | Lilongwe District Council | 25000000 | MWK | 2021-12-29T00:00:00Z | 2022-03-29T00:00:00Z | 90

## locations
id | locations/0/id | locations/0/description | locations/0/geometry/type | locations/0/geometry/coordinates | locations/0/address/locality | locations/0/address/region | locations/0/address/countryName
oc4ids-iuq5r5_179 | 164 | T/A Kalolo | Polygon | [[[33.430436,-13.930419],[33.430436,-13.930054],[33.430763,-13.930054],[33.430763,-13.930419],[33.430436,-13.930419]]] | LL | Central | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles | parties/0/contactPoint/faxNumber | parties/0/contactPoint/url
oc4ids-iuq5r5_179 | 22 | Lilongwe District Council | Lilongwe | Post Office Box 93, Lilongwe | Central | 0000 | Malawi | Lilongwe District Council | ldistrict@gov.mw | 09000000000 | procuringEntity;administrativeEntity
oc4ids-iuq5r5_179 | 51 | Malawi Government | Capital Hill | Lilongwe | Central Region | 0000 | Malawi | Malawi Government | info@malawi.gov.mw | 0000 | funder | 0000 | https://www.malawi.gov.mw