## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/maxExtentDate | assetLifetime/durationInDays | budget | completion/endDate | completion/endDateDetails | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_274 | Construction of Dzoole Police Unit (Administration Block) | Construction of Administration Block at Dzoole Police Unit | To provide housing to the Police Unit | construction | completion | 2025-05-22T15:33:29Z | 2023-02-15T00:00:00Z | 2023-06-14T00:00:00Z | 2023-06-30T00:00:00Z | 135 | socialHousing | 2023-02-15T00:00:00Z | 2073-02-15T00:00:00Z | 2073-04-04T00:00:00Z | 18311 | 0.00 | 2023-11-29T00:00:00Z | The project was completed after requesting 2 months of extension | The police unit has been completed and is being used | 70387617.74 | MWK

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_274 | 144 | contractSigned | Contract Agreement | Signed Contract for the construction of Dzoole Police uNit | https:// | application/pdf

## locations
id | locations/0/id | locations/0/description | locations/0/geometry/type | locations/0/geometry/coordinates | locations/0/address/streetAddress | locations/0/address/locality | locations/0/address/region | locations/0/address/postalCode | locations/0/address/countryName
oc4ids-iuq5r5_274 | 210 | Dowa West Constituency | Point | [33.96096,-13.674644] | Dzoole Trading Center, TA Dzoole | DO | Central | 0000 | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles | parties/0/contactPoint/url
oc4ids-iuq5r5_274 | 41 | Dowa District Council | Private Bag 2 | Dowa | Central | Dowa | Malawi | Dowa District Council | bandanoelsk@live.com | 0999632510 | procuringEntity
oc4ids-iuq5r5_274 | 45 | World Bank | 1818 H Street, NW Washington, DC 20433 USA | Washington, DC | District of Columbia | 20433 | United States of America (the) | World Bank | info@worldbank.org | +1 (202) 473-1000 | funder | https://www.worldbank.org
oc4ids-iuq5r5_274 | 224 | Rehema Building and Civil COntractors | Lumbadzi | Lilongwe | Central |  | Malawi | Rehema Building and Civil COntractors | email@email.com | 0000000000 | supplier