## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/maxExtentDate | assetLifetime/durationInDays | budget | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_282 | Construction of a classroom block at Mtuwakale primary school | construction of classroom block at Mtuwakale primary school | To reduce pupil to classroom ratio | construction | completion | 2024-02-29T09:12:09Z | 2023-01-13T00:00:00Z | 2023-04-13T00:00:00Z | 2023-05-13T00:00:00Z | 120 | 2023-04-13T00:00:00Z | 2073-04-13T00:00:00Z | 2093-04-13T00:00:00Z | 25568 | 0.00 | 2023-04-13T00:00:00Z | the project was completed on time | there was a bit of an increment in the project cost due to the additional quantities of foundation walls | Construction of a classroom block | construction of a two roomed classroom | 39883611.47 | MWK

## con_sum_suppliers
id | contractingProcesses/0/id | contractingProcesses/0/summary/suppliers/0/id | contractingProcesses/0/summary/suppliers/0/name
oc4ids-iuq5r5_282 | 116 | 281 | Ole-ole construction

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/maxExtentDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_282 | 116 | LDC/GESD/2022-23/CB/04GLOT5 | CONSTRUCTION OF CLASSROOM BLOCK AT MTUWAKALE | CONSTRUCTION OF CLASSROOM BLOCK AT MTUWAKALE | active | construction | 41500000 | MWK | 22 | Lilongwe District Council | 22 | Lilongwe District Council | 37976645.2 | MWK | 2023-01-13T00:00:00Z | 2023-04-13T00:00:00Z | 2023-05-31T00:00:00Z | 138

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/datePublished | documents/0/format | documents/0/pageStart | documents/0/pageEnd | documents/0/accessDetails | documents/0/author
oc4ids-iuq5r5_282 | 134 | contractSigned | Construction of Classroom block at Mtuwakale | Construction of Classroom block at Mtuwakale | https:// | 2023-01-10T00:00:00Z | application/pdf | 1 | 4 | contact DPW on +265999350819 | Sydney Chiphaka

## locations
id | locations/0/id | locations/0/description | locations/0/address/locality | locations/0/address/region | locations/0/address/postalCode | locations/0/address/countryName
oc4ids-iuq5r5_282 | 217 | T/A Njewa | LL | Central | 00000000 | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles | parties/0/contactPoint/url
oc4ids-iuq5r5_282 | 22 | Lilongwe District Council | Lilongwe | Post Office Box 93, Lilongwe | Central | 0000 | Malawi | Lilongwe District Council | ldistrict@gov.mw | 09000000000 | procuringEntity;administrativeEntity
oc4ids-iuq5r5_282 | 45 | World Bank | 1818 H Street, NW Washington, DC 20433 USA | Washington, DC | District of Columbia | 20433 | United States of America (the) | World Bank | info@worldbank.org | +1 (202) 473-1000 | funder | https://www.worldbank.org
oc4ids-iuq5r5_282 | 281 | Ole-ole construction | Lilongwe | Lilongwe |  |  | Malawi | Ole-ole construction | @gmail.com | 0000 | contractor;supplier