## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/maxExtentDate | assetLifetime/durationInDays | budget | completion/endDate | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_326 | Construction of Kameme EPA Office | The project will construct an office block for agricultural extension workers and provision of furniture | The project aims at improving the provision of agricultural extension services in the Kameme area as the extension workers will have offices within the area. This in turn is anticipated to improve agricultural production and improve household income for the farming family households. | construction | implementation | 2023-04-11T10:17:30Z | 2022-11-29T00:00:00Z | 2023-02-28T00:00:00Z | 2023-05-12T00:00:00Z | 164 | economy.agriculture;economy | 2023-05-12T00:00:00Z | 2053-05-05T00:00:00Z | 2063-05-12T00:00:00Z | 14610 | 0.00 | 2023-05-12T00:00:00Z | Construction of Substructure and slab works completed Construction of superstructure at ring beam level | 63398306 | MWK

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_326 | 383 | Contract/29/11/22 | Contract | The project contract between Chitipa District Council and Morogo Civil Construction for the construction of the Kameme EPA Office block | active | construction | 63398306 | MWK | 62 | Chitipa District Council | 62 | Chitipa District Council | 63398306 | MWK | 2022-12-06T00:00:00Z | 2023-03-06T00:00:00Z | 90

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_326 | 275 | contractSigned | Contract | Project contract document | https:// | application/pdf
oc4ids-iuq5r5_326 | 276 | defaultEvents | Picture | Construction of Kameme EPA Office block at ring beam level | https:// | image/jpeg

## locations
id | locations/0/id | locations/0/description | locations/0/address/locality | locations/0/address/region | locations/0/address/countryName
oc4ids-iuq5r5_326 | 421 | TA KAMEME | CT | Northern | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles | parties/0/contactPoint/faxNumber
oc4ids-iuq5r5_326 | 62 | Chitipa District Council | P.O. Box 1, Chitipa | Chitipa | Northern Region | 0000 | Malawi | Chitipa District Council | Email@email.com | 00000000 | procuringEntity;administrativeEntity
oc4ids-iuq5r5_326 | 236 | Marogo Civil & Building Contractors | Mchinji Boma | Mchinji | Central | Box 28 | Malawi | Marogo Civil & Building Contractors | marogo@gmail.com | 0880927578 | contractor | 0000