## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/durationInDays | budget | completion/endDate | completion/endDateDetails
oc4ids-iuq5r5_384 | Electrification of Malomo Rural Growth Centre Market | Constructing all infrastructure to allow for electricity connectivity. | To have access to electricity at the trading centre for diverse businesses that cater community members. | construction | completion | 2023-05-17T16:21:58Z | 2022-03-26T00:00:00Z | 2022-04-15T00:00:00Z | 20 | 0.00 | 2022-04-15T00:00:00Z | ubing Works, Fishing and Electrical Accessories Fittings, Poling Remaining : ESCOM Connections

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_384 | 149 | NS/IPDAC/22/RFQ/WKS/02 | Contract Agreement between Ntchisi District Council and Premium Construction | The Contract states that Premium Construction Company should execute the electrification of Malomo Market at Malamo Trading Centre | closed | construction | 16500000 | MWK | 20 | Ntchisi District Council | 20 | Ntchisi District Council | 19794767.5 | MWK | 2022-03-11T00:00:00Z | 2022-04-15T00:00:00Z | 35

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_384 | 159 | environmentalImpact | ESMP for Malamo Market electrification project | The document describes in detail the potential environmental and social impacts associated with the proposed sub project under electrification of Malomo market and outline mitigation measures required to address the identified impacts | https:// | application/vnd.openxmlformats-officedocument.wordprocessingml.document
oc4ids-iuq5r5_384 | 174 | contractSigned | Contract Agreement - NS & Premium Construction- Electrification of Malomo Rural Growth Centre Market | This is the signed Contract Agreement between Ntchisi District council and Premium Construction for the Electrification of Malomo Rural Growth Centre Market | https:// | application/msword

## locations
id | locations/0/id | locations/0/description | locations/0/address/locality | locations/0/address/region | locations/0/address/countryName
oc4ids-iuq5r5_384 | 309 | T/A Chilooko | NI | Central | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles
oc4ids-iuq5r5_384 | 20 | Ntchisi District Council | Box 1 | Ntchisi | Central | Malawi | Ntchisi District Council | email@email.com | 000000000 | procuringEntity;administrativeEntity