## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/maxExtentDate | assetLifetime/durationInDays | budget | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_535 | Construction of Makumbo satff house | The constrcution of the satff house at Makumbo will facilitate easy service delivery as the community will have readily available health personnel | It is meant to reduce avoidable death which are often due to long distance traveled in accessing the health services. | construction | completion | 2023-06-05T08:08:54Z | 2021-12-14T00:00:00Z | 2022-04-01T00:00:00Z | 2022-04-01T00:00:00Z | 108 | health | 2022-05-01T00:00:00Z | 2072-05-01T00:00:00Z | 2072-05-01T00:00:00Z | 18263 | 0.00 | 2022-04-01T00:00:00Z | The project was completed but not yet handled over to the community for utilization because the dispensary is still under construction. | Improved health services | The community will have no more problem of traveling long distance to acquire the health services | The community will have no more problem of traveling long distance to acquire the health services | 27699975.81 | MWK

## con_sum_ten_tenderers
id | contractingProcesses/0/id | contractingProcesses/0/summary/tender/tenderers/0/id | contractingProcesses/0/summary/tender/tenderers/0/name
oc4ids-iuq5r5_535 | 397 | 61 | Nkhatabay District Council

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/externalReference | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/procurementMethod | contractingProcesses/0/summary/tender/procurementMethodDetails | contractingProcesses/0/summary/tender/numberOfTenderers | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/maxExtentDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_535 | 397 | 536 | NB/DC/DDF/2021/22/10/1 | Construction of Makumbo satff house | Construction of Makumbo satff house | active | construction | open | lowestCost | 1 | 27699975.81 | MWK | 61 | Nkhatabay District Council | 61 | Nkhatabay District Council | 27699975.81 | MWK | 2022-01-14T00:00:00Z | 2022-05-14T00:00:00Z | 2022-05-14T00:00:00Z | 120

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_535 | 322 | contractAnnexe | Construction of Makumbo satff house | Construction of Makumbo satff house | https://ippi.mw/documents | image/jpeg

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/roles
oc4ids-iuq5r5_535 | 61 | Nkhatabay District Council | P.O. Box 1, Nkhata Bay | Nkhatabay | Northern Region | 0000 | Malawi | Nkhatabay District Council | Email@email.com | 00000000 | tenderer;procuringEntity;administrativeEntity