## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/durationInDays | budget | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_584 | CONSTRUCTION OF 6 BOREHOLES | BOREHOLE CONSTRUCTION | WATER SUPPLY | construction | completion | 2023-07-04T06:54:15Z | 2022-11-22T00:00:00Z | 2023-03-23T00:00:00Z | 121 | 0.00 | 2023-03-23T00:00:00Z | COMPLETED | THERE WAS NO VARIATION OF COSTS | BOREHOLES | THE PROJECT WAS COMPLETED IN TIME | 26080000 | MWK