## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/durationInDays | sector | assetLifetime/startDate | budget | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_631 | Construction of Boma Shops | Constructing 5 shops and completing toilet block that was at window level. | Revenue generation for the council | construction | completion | 2023-09-06T08:50:56Z | 2023-01-18T00:00:00Z | 2023-05-18T00:00:00Z | 120 | economy | 2023-06-30T00:00:00Z | 0.00 | 2023-06-30T00:00:00Z | Completed | Within contract amount | Completed | Completed. Awaiting handover | 60652069.18 | MWK

## contractingProcesses
id | contractingProcesses/0/id | contractingProcesses/0/summary/ocid | contractingProcesses/0/summary/title | contractingProcesses/0/summary/description | contractingProcesses/0/summary/status | contractingProcesses/0/summary/nature | contractingProcesses/0/summary/tender/costEstimate/amount | contractingProcesses/0/summary/tender/costEstimate/currency | contractingProcesses/0/summary/tender/procuringEntity/id | contractingProcesses/0/summary/tender/procuringEntity/name | contractingProcesses/0/summary/tender/administrativeEntity/id | contractingProcesses/0/summary/tender/administrativeEntity/name | contractingProcesses/0/summary/contractValue/amount | contractingProcesses/0/summary/contractValue/currency | contractingProcesses/0/summary/contractPeriod/startDate | contractingProcesses/0/summary/contractPeriod/endDate | contractingProcesses/0/summary/contractPeriod/durationInDays
oc4ids-iuq5r5_631 | 462 | MW-MDC 318973-CW-RFQ | Construction of shops | Signed contract | active | construction | 60699999.76 | MWK | 369 | Mwanza District Council | 369 | Mwanza District Council | 60699999.76 | MWK | 2023-01-18T00:00:00Z | 2023-05-18T00:00:00Z | 120

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_631 | 377 | contractSigned | Contract Agreement for Boma shops | Signed contract for Construction of Boma shops | https:// | application/pdf

## locations
id | locations/0/id | locations/0/description | locations/0/address/locality | locations/0/address/region | locations/0/address/countryName
oc4ids-iuq5r5_631 | 534 | TA Kanduku, GVH Mchotseni | MW | Southern | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/contactPoint/url | parties/0/roles
oc4ids-iuq5r5_631 | 96 | Fidelis Building Contractors | P.O. Box 330, Zomba | Zomba | Southern Region | 0000 | Malawi | Fidelis Building Contractors | 0000 | 0000 | https://0000 | contractor
oc4ids-iuq5r5_631 | 369 | Mwanza District Council | Mwanza | Mwanza |  |  | Malawi | Mwanza District Council | @gmail.com | 000 |  | procuringEntity;administrativeEntity