## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/maxExtentDate | assetLifetime/durationInDays | budget | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_708 | Construction of Waluma CDSS School Block 2 and furnishing it with students desks and teachers chairs and desks | The project will involve the Construction of Waluma School block 2 and furnishing it with Desks | To ease access to education to learners within the surrounding community. | construction | completion | 2023-09-06T17:29:59Z | 2022-11-07T00:00:00Z | 2023-01-31T00:00:00Z | 2023-02-05T00:00:00Z | 90 | education | 2022-11-07T00:00:00Z | 2023-02-08T00:00:00Z | 2023-09-06T00:00:00Z | 303 | 0.00 | 2023-01-31T00:00:00Z | The project is almost 95% completion | Fifty eight million nine hundred and forty thousand four hundred eighty six kwacha forty six tambala | 1 classroom block constructed and 120 desks will be provided | 1 classroom block constructed and 120 desks will be provided | 58940486.46 | MWK