## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/durationInDays | assetLifetime/durationInDays | budget | completion/endDate | completion/endDateDetails | completion/finalValueDetails
oc4ids-iuq5r5_747 | Construction of 6No Blocks of 2bedroomed House at Ngumbe | 6No semi detached blocks of 2 bedrooms | Providing shelter, safety and affordable houses to the nation | construction | completion | 2023-09-07T12:59:27Z | 2018-05-02T00:00:00Z | 2018-11-02T00:00:00Z | 184 | 184 | 0.00 | 2022-04-28T00:00:00Z | Works delayed due to late payment of interim certificates to the contractor | 210,206,316.85