## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | assetLifetime/startDate | assetLifetime/endDate | assetLifetime/maxExtentDate | assetLifetime/durationInDays | budget | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_81 | CHIMATIRO MATERNITY WING | CONSTRUCTION OF CHIMATIRO MATERNITY WING, SEPTIC TANK, PLACENTA PIT AND WATER TANK | IMPROVING ACCESS TO MATERNAL HEALTH | construction | completion | 2023-09-06T12:42:28Z | 2021-12-13T00:00:00Z | 2022-04-30T00:00:00Z | 2022-09-30T00:00:00Z | 291 | health | 2022-10-03T00:00:00Z | 2052-12-27T00:00:00Z | 2062-08-25T00:00:00Z | 14571 | 0.00 | 2023-09-01T00:00:00Z | The project was completed within the implementation period | completed with additional cost | Completed with additional External works | Main clinic block, placenta pit, ash pit, incinerator | 67344480.52 | MWK

## locations
id | locations/0/id | locations/0/description | locations/0/address/streetAddress | locations/0/address/locality | locations/0/address/region | locations/0/address/postalCode | locations/0/address/countryName
oc4ids-iuq5r5_81 | 87 | TA SAWALI/CHIMATIRO VDC/ NEAR SAWALI TRADING CENTRE/NKHONDE WARD/ BALAK CENTRAL EAST | SAWALI TRADING CENTRE | BA | Southern | 1 | Malawi

## parties
id | parties/0/id | parties/0/name | parties/0/address/streetAddress | parties/0/address/locality | parties/0/address/region | parties/0/address/postalCode | parties/0/address/countryName | parties/0/contactPoint/name | parties/0/contactPoint/email | parties/0/contactPoint/telephone | parties/0/contactPoint/faxNumber | parties/0/contactPoint/url | parties/0/roles
oc4ids-iuq5r5_81 | 69 | Balaka District Council | off balaka main road next to Meru filling station | Balaka | South | P/Bag 1 | Malawi | Balaka District Council | gamafrancis6@gmail.com | 265 1 552 049 | 265 1 552 050/790 | http://balakadistrictcouncil.com | procuringEntity
oc4ids-iuq5r5_81 | 137 | Mathews Phiri Civil Engineering | P.O. Box 314, Zomba | Zomba | Southern Region | 0000 | Malawi | Mathews Phiri Civil Engineering | 0000 | +265995219619 |  | https://0000 | supplier