## main
id | title | description | purpose | type | status | updated | period/startDate | period/endDate | period/maxExtentDate | period/durationInDays | sector | budget | completion/endDate | completion/endDateDetails | completion/finalValueDetails | completion/finalScope | completion/finalScopeDetails | completion/finalValue/amount | completion/finalValue/currency
oc4ids-iuq5r5_816 | Rehabilitation of Female Ward at Dowa District Hospital | Rehabilitation of Female Ward at Dowa District Hospital | Improve Health Service Delivery | rehabilitation | completion | 2025-03-10T18:27:03Z | 2023-06-26T00:00:00Z | 2024-02-25T00:00:00Z | 2024-06-08T00:00:00Z | 348 | health | 0.00 | 2024-02-25T00:00:00Z | The Project was Completed and handed over to the community | due to price fractuation the tendered sum was adjusted upwards | The Female ward was rehabilitated | All works have been completed and the ward is in use | 213215962.44 | MWK

## documents
id | documents/0/id | documents/0/documentType | documents/0/title | documents/0/description | documents/0/url | documents/0/format
oc4ids-iuq5r5_816 | 408 | awardNotice | Notice to Award Contract | A contract award notice to the winning contractor | https:// | application/pdf
oc4ids-iuq5r5_816 | 409 | biddingDocuments | Bidding Documents | All bidding Information related to the LOT | https:// | application/pdf
oc4ids-iuq5r5_816 | 410 | billOfQuantity | BOQ | BOQ for the LOT | https:// | application/vnd.ms-excel
oc4ids-iuq5r5_816 | 411 | completionCertificate | Practical Completion Certificate | Certification of completed works | https:// | application/pdf

## locations
id | locations/0/id | locations/0/description | locations/0/address/streetAddress | locations/0/address/locality | locations/0/address/region | locations/0/address/countryName
oc4ids-iuq5r5_816 | 577 | Dowa District Hospital | Along Dowa Main Road to Wenera | DO | Central | Malawi