**

**M’MBELWA DISTRICT COUNCIL**

**Site meeting report**

|  |  |
| --- | --- |
| **Name of Activity:** | Site meeting report- Lweya Bridge Construction |
| **Date of Activity**: | 02nd January 2022 | **Type of Activity:** | Field visit |
| **Location:** | Mzalangwe (T/A Chindi, Mzimba Hora) |  |  |
| **Compiled by:** | * R. Moyo
 |  |  |
| **Participants**  | **Name**1. R. Moyo
 | **Designation**R/S |  |
| **Programme** |
| **Purpose of site visit:**1. To appraise progress of works at Luweya Bridge
 |
| **Project status**:* Luweya Bridge Construction is a project initially conceived under GESD and works commenced on 28/12/2021.
* Works on the project are being undertaken by Mtalimanja Civil Contractors. Works Progress have reached 40 % completion.
* The contractor had finished removing old beams and had started fixing of abatement caps and pier caps.
* The quality of works is generally good.

  |
| **Observations**1. The length of the Bridge is 27M, 3Span with a width of 3.8M (as described in the BOQ).
2. Quarry used is of poor quality. i.e., full of impurities and size being small.
3. There is lot of artisans on the construction site.
 |
|  **Action Items:** |
| **Action** | **Responsible** | **Due** |
| 1. The Contractor to produce test results of material samples
 | Contractor | ASAP |
| 1. The Contractor to improve on the quality of quarry stone used.
 | Contractor | ASAP |
| 1. The Contractor to provide PPEs for the laborer’s working on the site
 | Contractor | ASAP |